## Slide 1: Board Priorities (2013-2015) Semi-Annual Progress Report 13/14 Mid Year
Submitted: December 2, 2013
Prepared by: Charlie Price

## Slide 2: Board Priorities 2013-2015 Reporting Schedule*
Report | POP Covered | Updates Due | Submit to Board | Board Meeting
13/14 MID | MAY - OCT | 11/08/13 | 12/02/13 | 12/12/13
13/14 EOY | NOV-APR | 05/09/13 | 05/23/13 | 06/05/14
14/15 MID |  |  |  | 
14/15 EOY |  |  |  | 
*Dates subject to change based on rolling wave planning and Division Calendar development.

## Slide 3: 2013-15 Priorities Status Overview
Period | Good | Warning | Danger | Complete
13/14 MID | 8 | 8* | 0 | 1
13/14 EOY |  |  |  | 
14/15 MID |  |  |  | 
14/15 EOY |  |  |  | 
17 Total projects
  Matt Haas – 5
  Billy Haun – 5
  Dean Tistadt – 2
  Vince Scheivert - 2
  Matt/Dean – 3
*All Yellow Projects are due to pending budget direction.
Legend | 
 | GOOD: On-time or ahead of schedule and meets all quality expectations.
 | WARNING: Moving forward but some deadlines have been missed and/or deliverables not met. Overall project scope has not been compromised, but some areas of concern have been identified and must be addressed to avoid failure.
 | DANGER: Not progressing.
 | Complete
!

## Slide 4
One Student-Centered Goal
All students will graduate having actively mastered the lifelong-learning skills they need to succeed as 21st century learners, workers, and citizens.
Objective 1
We will engage every student
Objective 2 We will implement balanced assessments
Objective 3 We will improve opportunity and achievement
Objective 4
We will create and expand partnerships
Objective 5
We will optimize resources

## Slide 5: Objective 1: We Will Engage Every Student

## Slide 6
1.1.1 Cross Functional design team (Innovation Team) |  | 
 | 13/14 MID | Team met in December to for initial charge and meeting plan. Plan implementation affected by budget direction.
 | 13/14 EOY | 
 | 14/15 MID | 
 | 14/15 EOY | 
Innovation Team - Matt Haas
1.1 Define, develop, and implement effective teaching practices that maximize rigor and meaningful engagement for all students.

## Slide 7
1.1.2 Update Learning Walk Tool |  | 
 | 13/14 MID | Gathering feedback from Teachers and Administrators on desired updates. This will be part of the cross-functional team work cited in 1.11. The team has had an initial meeting in December for planning.
 | 13/14 EOY | 
 | 14/15 MID | 
 | 14/15 EOY | 
 | 13/14 MID | 
1.1 Define, develop, and implement effective teaching practices that maximize rigor and meaningful engagement for all students.
Learning Walk Tool - Matt Haas

## Slide 8
1.2.1 Conduct a needs assessment & develop a budget initiative. 1.2.2 Focused professional development plan for 7 pathways. |  | 
 | 13/14 MID | Needs assessment in process; due to complete by Feb 3, 2014. Implementation contingent on budget direction.
 | 13/14 EOY | 
 | 14/15 MID | 
 | 14/15 EOY | 
Professional Development - Billy Haun
1.2 Develop division-wide master framework for contemporary professional development and training that optimizes our workforce and addresses the essential competencies needed by teachers, administrators, and classified staff.

## Slide 9
1.2.3 Update performance appraisal program to include a standards-based digital portfolio approach for all licensed staff. |  | 
 | 13/14 MID | Implementation contingent on budget direction for Paperless evaluation System/Appraisal System.
 | 13/14 EOY | 
 | 14/15 MID | 
 | 14/15 EOY | 
Performance Appraisal System - Matt Haas
1.2 Develop division-wide master framework for contemporary professional development and training that optimizes our workforce and addresses the essential competencies needed by teachers, administrators, and classified staff.

## Slide 10
1.3.1 Define the standards of a “contemporary learning space.” 1.3.2 Conduct an assessment of all schools to determine current state. 1.3.3 Develop a multi-year plan to convert spaces to contemporary learning space standards. |  | 
 | 13/14 MID | Using Agnor Hurt design imperatives as definition of “Contemporary Learning Space. School Assessments to begin in February. This will be part of the cross-functional team work cited in 1.11. The team has had an initial meeting in December for planning.
 | 13/14 EOY | 
 | 14/15 MID | 
 | 14/15 EOY | 
Contemporary Learning Space - Matt Haas / Dean Tistadt
1.3 Integrate the use of contemporary learning spaces and supportive technologies into the instructional program delivery.

## Slide 11: Objective 2: We will implement Balanced Assessments.

## Slide 12
2.1.1 Align the Division’s assessment matrix to the LLC. 2.1.2 Develop rubrics for LLC. 2.1.3 Define elements/expectations/procedures for student portfolio. |  | 
 | 13/14 MID | Performance tasks for LLCs have been vetted. Vertical teams & coaches developing rubrics for LLC Performance Tasks.
 | 13/14 EOY | 
 | 14/15 MID | 
 | 14/15 EOY | 
Performance Task Assessments - Billy Haun
2.1 Define and communicate the Division’s specific measures (Performance Tasks) for mastery of lifelong-learning competencies and student success.

## Slide 13
2.2.1Expand PD opportunities for teachers and administrators on balanced assessment systems. 2.2.2 Create a school level report for each LLC based on Student Portfolios. |  | 
 | 13/14 MID | Finalizing project schedule and creating portfolio prototypes.
 | 13/14 EOY | 
 | 14/15 MID | 
 | 14/15 EOY | 
LLC Student Portfolios - Vince Scheivert
2.2 Implement performance-based assessments/tasks and grading practices to create a balanced learning system that measures ACPS outcomes for student success.

## Slide 14: Objective 3: We will improve opportunity and achievement.

## Slide 15
3.1.1 Measure and report student and enrollment group performance on key metrics for work and college readiness from k-12 including student performance on ACPS division-wide performance task assessments. |  | 
 | 13/14 MID | Priority 2.1 Performance Task Assessment Rubrics are under development. Once that is complete we will be able to gather and report data.
 | 13/14 EOY | 
 | 14/15 MID | 
 | 14/15 EOY | 
Metrics - Vince Scheivert
3.1 Prepare all students for successful transition to the next grade in their PK-12 experience.

## Slide 16
3.1.2 Create and implement a standard transition activity plan across the school division for elementary to middle and middle to high school transitions. |  | 
 | 13/14 MID | Student transition plans are being framed under the three areas of Guidance: Academic, Personal/Social, and Career. Working teams of counselors, coaches, and teachers are being formed.
 | 13/14 EOY | 
 | 14/15 MID | 
 | 14/15 EOY | 
Student Transition Plan - Billy Haun
3.1 Prepare all students for successful transition to the next grade in their PK-12 experience.

## Slide 17
3.2.1 Develop a proposal/plan. 3.2.2 Create a logic map. 3.2.3 Evaluate Models. 3.2.4 Construct a budget initiative. 3.2.5 Target a pilot. 3.2.6 Obtain funding for Division-wide implementation. |  | 
 | 13/14 MID | Pending board direction on budget initiative.
 | 13/14 EOY | 
 | 14/15 MID | 
 | 14/15 EOY | 
World Languages Program - Billy Haun
3.2 Implement a robust, Division-wide PK-12 World Languages Program.

## Slide 18: Objective 4: We will create and expand partnerships.

## Slide 19
4.1.1 Study and report our present state. 4.1.2 Create and implement an action plan to enhance field trip opportunities. 4.1.3 Create and implement and action plan to enhance mentoring and internship opportunities. |  | 
 | 13/14 MID | Current state assessment in process; planned completion in February.
 | 13/14 EOY | 
 | 14/15 MID | 
 | 14/15 EOY | 
Mentorship / Internship - Billy Haun
4.1 Implement a comprehensive mentorship and internship program and expand field trip opportunities to provide real-world learning experiences for all students’ success.

## Slide 20
4.2.1 Implement Division’s Strategic Communications Plan. 4.2.2 Create and use a survey calendar to gather feedback from our larger community and internal and external stakeholder groups. 4.2.3 Define “levels/purpose” of partnerships with the school division, quantify and report our numbers of partners and our shared activities annually. |  | 
 | 13/14 MID | Survey calendar under development. Some aspects of the Division’s Communication Plan is pending budget direction.
 | 13/14 EOY | 
 | 14/15 MID | 
 | 14/15 EOY | 
Community Support - Matt Haas
4.2 Invest the full community in supporting student achievement and outcomes for all students’ success.

## Slide 21: Objective 5: We will optimize resources

## Slide 22
5.1.1 Sustain effective practices from the Safe Schools / Healthy Students Grant. 5.1.2 Enact the Governor’s safety task force directives and policies. |  | 
 | 13/14 MID | Sustainment plan in place pending budget direction for Safety Coordinator position. Division Safety Team had first meeting in December.
 | 13/14 EOY | 
 | 14/15 MID | 
 | 14/15 EOY | 
Safety - Matt Haas / Dean Tistadt
5.1 Ensure the health and safety of the school community.

## Slide 23
5.1.3 Assess and improve our health services and education for students. 5.1.4 Assess and improve our health services and education for employees. |  | 
 | 13/14 MID | 5.1.3 Health Advisory Board continuously monitors and develops / recommends improvement initiatives. Next meeting in January of Board and Concussion Management Team. Full time Nurse initiative pending budget direction. 5.1.4 Establishing a cross-team with Leanne Knox regarding health services for employees. Team met in December.
 | 13/14 EOY | 
 | 14/15 MID | 
 | 14/15 EOY | 
Health Services - Matt Haas
5.1 Ensure the health and safety of the school community.

## Slide 24
5.2.1 Ensure that the budget initiatives are aligned with the Horizon 2020 Strategic Plan during annual budget process and mid-year adjustments. 5.2.2 Ensure that all budget-related documents include language that relates specific funding requests to specific objectives and strategies within the strategic plan. |  | 
 | 13/14 MID | Policies and procedures are in place to ensure alignment of budget to Strategic Plan.
Budget/Strategy Alignment - Dean Tistadt
5.2 Optimize the use of fiscal resources in support of the Division’s strategic plan and operations.

## Slide 25
5.3.1 Develop a plan with a logic model and budget proposal. |  | 
 | 13/14 MID | This will be part of the cross-functional team work cited in 1.11. The team has had an initial meeting in December for planning.
 | 13/14 EOY | 
 | 14/15 MID | 
 | 14/15 EOY | 
High School of the Future - Matt Haas / Dean Tistadt
5.3 Design the high school of the future.