## Slide 1: Bond Referendum Update
November 10, 2016

## Slide 2: Results
Chart: 
| Yes | No
Votes | 40193 | 14480
No:
14,480
Yes:
40,193

## Slide 3
FY 18 CIP Development Flowchart
Dept/Agency
Studies
Submittals
FRC
Review
2 Boards
Review #1
Board of
Supervisors
Approved
CIP
OFD/OMB
Review
TRC
Review
Executive Office
OC
Review
Executive
Office
FRC
Review
Planning Commission
CIP - Capital Improvement Plan (Five-Year Period)
FRC-Financial Review Committee
LRPC-Long Range Planning Committee
OC-Oversight Committee
OFD-Office of Facilities Development
OMB-Office of Management & Budget
TRC-Technical Review Committee
August | September | October | November…
…Nov. | December | January - February | February - April | April
OC REPORT
Executive Office
Board of Supervisors
School Board
Planning Commission

## Slide 4
Project | 2017 |  |  |  | 2018 |  |  | 
 | Winter | Spring | Summer | Fall | Winter | Spring | Summer | Fall
Baker Butler Security | Design/Bid |  | Construct |  |  |  |  | 
Scottsville Security | Design/Bid |  | Construct |  |  |  |  | 
Henley Security |  |  |  |  | Design/Bid |  | Construct | 
Murray HS Security |  |  |  |  | Design/Bid |  | Construct | 
Woodbrook Addition/Mod. | ◄ Design/Bid |  | Construct |  |  |  |  | 
WAHS Science Addition/Mod. |  |  |  | Design/Bid |  |  | Construct ► | 
Learning Space Modernization | Design Ph. 1 |  | Construct Ph. 1 ($3.3M) |  | Design Ph. 2 |  | Construct Ph. 2 ($7.6M) | 
Redistricting

## Slide 5
Project | 2017 |  |  |  | 2018 |  |  | 
 | Winter | Spring | Summer | Fall | Winter | Spring | Summer | Fall
Baker Butler Security | Design/Bid |  | Construct |  |  |  |  | 
Scottsville Security | Design/Bid |  | Construct |  |  |  |  | 
Henley Security |  |  |  |  | Design/Bid |  | Construct | 
Murray HS Security |  |  |  |  | Design/Bid |  | Construct | 
Woodbrook Addition/Mod. | ◄ Design/Bid |  | Construct |  |  |  |  | 
WAHS Science Addition/Mod. |  |  |  | Design/Bid |  |  | Construct ► | 
Learning Space Modernization | Design Ph. 1 |  | Construct Ph. 1 ($3.3M) |  | Design Ph. 2 |  | Construct Ph. 2 ($7.6M) | 
Redistricting Study

## Slide 6
Project | 2017 |  |  |  | 2018 |  |  | 
 | Winter | Spring | Summer | Fall | Winter | Spring | Summer | Fall
Baker Butler Security | Design/Bid |  | Construct |  |  |  |  | 
Scottsville Security | Design/Bid |  | Construct |  |  |  |  | 
Henley Security |  |  |  |  | Design/Bid |  | Construct | 
Murray HS Security |  |  |  |  | Design/Bid |  | Construct | 
Woodbrook Addition/Mod. | ◄ Design/Bid |  | Construct |  |  |  |  | 
WAHS Science Addition/Mod. |  |  |  | Design/Bid |  |  | Construct ► | 
Learning Space Modernization | Design Ph. 1 |  | Construct Ph. 1 ($3.3M) |  | Design Ph. 2 |  | Construct Ph. 2 ($7.6M) | 
Redistricting Study

## Slide 7
Project | 2017 |  |  |  | 2018 |  |  | 
 | Winter | Spring | Summer | Fall | Winter | Spring | Summer | Fall
Baker Butler Security | Design/Bid |  | Construct |  |  |  |  | 
Scottsville Security | Design/Bid |  | Construct |  |  |  |  | 
Henley Security |  |  |  |  | Design/Bid |  | Construct | 
Murray HS Security |  |  |  |  | Design/Bid |  | Construct | 
Woodbrook Addition/Mod. | ◄ Design/Bid |  | Construct |  |  |  |  | 
WAHS Science Addition/Mod. |  |  |  | Design/Bid |  |  | Construct ► | 
Learning Space Modernization | Design Ph. 1 |  | Construct Ph. 1 ($3.3M) |  | Design Ph. 2 |  | Construct Ph. 2 ($7.6M) | 
Redistricting Study