## Slide 1
DESIGN DEVELOPMENT
Albemarle County Public Schools
November 9, 2017
WAHS SCIENCE LABS
ADDITION AND MODERNIZATION

## Slide 2
PROJECT TEAM
Albemarle County Public Schools
Contact: Sheila Hoopmann + Matt Wertman
shoopmann@albemarle.org
mwertman@albemarle.org
VMDO Architects
200 E Market St.
Charlottesville, VA 22902
(434)296-5684
www.vmdo.com
Contact: Ken Thacker
kthacker@vmdo.com
Lawrence Perry & Associates
15 E. Salem Avenue, SE, Suite 101
Roanoke, Virginia 24011
(540)342-1816
lpa-inc.com
Contact: Rick Hughes
RHughes@lpa-inc.com
Timmons Group
608 Preston Avenue, Suite 200
Charlottesville, VA 22903
(434)327-1668
www.timmons.com
Contact: Craig Kotarski
Craig.Kotarski@timmons.com
Fox + Associates, PC
12085 Gayton Road
Richmond, VA 23238
(804)750-2085
www.foxengineers.com
Contact: John Ireland
jireland@foxengineers.com
OWNER:
ARCHITECT:
MEP ENGINEER:
CIVIL ENGINEER:
STRUCTURAL ENGINEER:

## Slide 3
PROJECT DESCRIPTION:
PROJECT OVERVIEW
ORIGNAL Scope:
10,000 SF, 2-story Addition
8,000 SF Renovation
3,000 SF “Modernization”
Miscellaneous “daylighting” in (7) rooms
Budget:
$4.9 million
Schedule:
Phase I renovation completion: Fall 2018
Phase II renovation / addition completion: Fall 2019
CURRENT Scope:
7,900 SF, 2-story Addition
8,000 SF Renovation and Modernization
½ acre Outdoor Learning Space (Note: 32 parking spaces will be eliminated)
Miscellaneous “daylighting” in (7) rooms
Budget:
$4.9 million
Schedule:
Phase I renovation completion: Fall 2018
Phase II renovation / addition completion: Fall 2019

## Slide 4
SCHEDULE and BUDGET:
1. PROJECT STATUS
We are ON BUDGET according to our reconciled Schematic Design Phase cost estimate.
We are ON SCHEDULE; currently in the Design Development phase, roughly half-way through the overall planning process.

## Slide 5
1. PROJECT STATUS

## Slide 6
1. PROJECT STATUS
NOV 09 | School Board Presentation | Design Development
NOV 13 | Design Development #3 | Admin + Teachers ¦ CTE
NOV 14 | DD Teacher Workshop #2 | Teachers + Ray ¦ Discussion + Survey
NOV 28 | DD Teacher Workshop #2 | Teachers + Ray ¦ Development of Ideas
DEC 4 | Design Development #4 | Admin + Teachers ¦ Medium/high Intensity, sinks, storage, furniture
DEC 12 | DD Teacher Workshop | TBD
JAN 08 | Design Development #5 | Admin ¦ Technology, Add Alts, Construction Phasing
JAN 29 | Design Development #6 | Finalize Design Development
FEB 22 | Documents Released for Bidding | Concludes Design Development
REMAINING SCHEDULE:

## Slide 7
CONSULTANT INVOLVEMENT:
2. CONSULTANT INVOLVEMENT
Civil engineers are preparing for County site plan review.
MEP Engineers are investigating existing conditions, paying particular attention to above-ceiling conditions.
Lab planning consultant meetings will be held with the science teachers in the coming weeks.

## Slide 8
3. TEACHER INPUT
FIRST FLOOR
SECOND FLOOR
MEDIUM INTENSITY LAB
HIGH INTENSITY LAB
PROJECT ROOM / BREAKOUT SPACE
PREP ROOMS
TEACHER OFFICE

## Slide 9
4. SCOPE CHANGES
Omitted water storage cistern to feed storm water learning gardens.
Limited scope of interior renovations but still over what had initially been identified.
Request to add courtyard landscaping and new exterior doors.
SCOPE CHANGES SINCE SCHEMATIC DESIGN APPROVAL:
1
2
3
4

## Slide 10
LOOKING AHEAD:
5. LOOKING AHEAD
Meeting with CTE faculty next week.
On-going design review meetings with administrators and faculty are planned through January.
Confirming budget status with DD estimate later this month.
Documents will go out for bidding on February 22, 2018.

## Slide 11
SITE PLAN

## Slide 12
FIRST FLOOR PLAN

## Slide 13
SECOND FLOOR PLAN

## Slide 14
SECOND FLOOR PLAN

## Slide 15
PICTORIAL VIEWS
ADDITION | INTERIOR VIEW OF LEARNING LAB ONE